## Project Status
Status Key for Dropdowns
ROADBLOCK / OVERAGE
POTENTIAL RISKS / DELAYS
ON TRACK
Report Date | Milestone # |  | Your Name
2019-05-30 | 4 | Abdullah
PROJECT STATUS THIS WEEK
OVERALL PROJECT STATUS | ON TRACK | SUMMARY | GUI Completed
MILESTONES
Added Entry boxes and buttons to Add/Update/Delete coin
Added color schema and hoover effects to the table for visual aid
Key Accomplishments
DESCRIPTIONS
Created a table with header and body section
imported request module to access the link for CoinMarketAPI
imported Json module to save data from CoinMarketAPI into a dictionary variable called api
used the grid layout manegment to create a table with data
Added a button (with image) that refreshes table content and display up-to-date coin data
Planned Acccomplishments for next Report
Start on using sqlite3 db
Connect the db into the GUI app and implement CRUD operation through the app